## Capstone Gantt Chart
LIBRALINK: LIBRARY MANAGEMENT & BORROWING SYSTEM
Capstone Project Development Schedule (18 Weeks ¦ Aug 2026 - Dec 2026)
Task ID | WBS & Task Description | Assigned Lead / Role | Start Week | End Week | Duration (Wks) | Progress (%) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
[7 empty] | Aug 17 - Aug 21 | Aug 24 - Aug 28 | Aug 31 - Sep 04 | Sep 07 - Sep 11 | Sep 14 - Sep 18 | Sep 21 - Sep 25 | Sep 28 - Oct 02 | Oct 05 - Oct 09 | Oct 12 - Oct 16 | Oct 19 - Oct 23 | Oct 26 - Oct 30 | Nov 02 - Nov 06 | Nov 09 - Nov 13 | Nov 16 - Nov 20 | Nov 23 - Nov 27 | Nov 30 - Dec 04 | Dec 07 - Dec 11 | Dec 14 - Dec 18
PHASE 1: PROJECT INITIATION & REQUIREMENTS ANALYSIS
1.1 | Project Topic Proposal & Approval | Project Manager / Lead | 1 | 2 |  | 100% | bar: W1 to W18
1.2 | Stakeholder Interviews & Library Needs Assessment | System Analyst | 1 | 2 |  | 100% | bar: W1 to W18
1.3 | Software Requirements Specification (SRS) | Technical Writer / Lead | 2 | 3 |  | 100% | bar: W1 to W18
1.4 | Feasibility Study & Technology Stack Evaluation | Full Stack Developer | 2 | 3 |  | 100% | bar: W1 to W18
1.5 | Milestone 1: Project Plan & Scope Baseline Sign-off | All Members & Adviser | 3 | 3 |  | 100% | W3: ◆ MILESTONE
PHASE 2: SYSTEM ARCHITECTURE & UI/UX DESIGN
2.1 | ERD, Schema & MySQL Relational DB Modeling | Database Engineer | 3 | 5 |  | 100% | bar: W1 to W18
2.2 | REST API Contract & Endpoint Specification | Backend Developer | 4 | 5 |  | 100% | bar: W1 to W18
2.3 | Figma UI/UX Mockups (Student & Librarian Portals) | UI/UX Designer | 4 | 6 |  | 100% | bar: W1 to W18
2.4 | Navigation, Design System & Tailwind Theme Setup | Frontend Developer | 5 | 6 |  | 100% | bar: W1 to W18
2.5 | Milestone 2: System Architecture & Prototype Review | Adviser & Panel | 6 | 6 |  | 100% | W6: ◆ MILESTONE
PHASE 3: CORE BACKEND & DATABASE IMPLEMENTATION (Node.js/Express)
3.1 | Node.js Express Project Scaffolding & DB Pool Connection | Backend Developer | 6 | 7 |  | 100% | bar: W1 to W18
3.2 | JWT Authentication, Roles (Student/Librarian/Admin) | Backend Developer | 7 | 8 |  | 100% | bar: W1 to W18
3.3 | Book Catalog CRUD & Search/Filter API Endpoints | Backend Developer | 8 | 9 |  | 100% | bar: W1 to W18
3.4 | Borrowing, Return, Reservation & Due-Date Rules Engine | Backend Developer | 9 | 11 |  | 90% | W9: 90%; W10: 90%; W11: 90%
3.5 | Announcement, Feedback & Activity Log APIs | Backend Developer | 10 | 11 |  | 90% | W10: 90%; W11: 90%
PHASE 4: FRONTEND CLIENT & PORTAL DEVELOPMENT (React + Vite)
4.1 | Auth Views: Login, Register, College/Department Pickers | Frontend Developer | 7 | 8 |  | 100% | bar: W1 to W18
4.2 | Student Portal: Home, Book Catalog, Wishlist & Search | Frontend Developer | 8 | 10 |  | 95% | W8: 95%; W9: 95%; W10: 95%
4.3 | Student Borrowing Tracking: Active, History & Overdues | Frontend Developer | 10 | 11 |  | 90% | W10: 90%; W11: 90%
4.4 | Librarian Dashboard: Borrower Drawer & Issue/Return Ops | Full Stack Developer | 10 | 12 |  | 85% | W10: 85%; W11: 85%; W12: 85%
4.5 | Admin Panel: Analytics, User Roles & System Settings | Full Stack Developer | 11 | 13 |  | 75% | W11: 75%; W12: 75%; W13: 75%
PHASE 5: ADVANCED FEATURES & HARDWARE INTEGRATION
5.1 | QR Code Generation & Scanner for Fast Checkout/Checkin | Full Stack Developer | 12 | 14 |  | 70% | W12: 70%; W13: 70%; W14: 70%
5.2 | Real-time WebSockets Notifications (Due & Alerts) | Backend Developer | 13 | 14 |  | 60% | W13: 60%; W14: 60%
5.3 | Interactive Library Floor Map (Leaflet / Location Guide) | Frontend Developer | 13 | 15 |  | 50% | W13: 50%; W14: 50%; W15: 50%
5.4 | Milestone 3: Complete Beta Release & Demo Walkthrough | Capstone Team | 14 | 14 |  | 70% | W14: ◆ MILESTONE
PHASE 6: SYSTEM TESTING, QA & USER ACCEPTANCE (UAT)
6.1 | Unit & Integration Testing (API Endpoints & DB Queries) | QA / Backend | 14 | 15 |  | 40% | W14: 40%; W15: 40%
6.2 | User Acceptance Testing (UAT) with College Librarians | QA / System Analyst | 15 | 16 |  | 20% | W15: 20%; W16: 20%
6.3 | Bug Fixing, UI Polish, Performance & Security Audit | Full Stack Team | 15 | 17 |  | 30% | W15: 30%; W16: 30%; W17: 30%
PHASE 7: DOCUMENTATION, DEPLOYMENT & CAPSTONE DEFENSE
7.1 | Thesis Final Manuscript (Chapters 1 - 5 Completion) | All Members | 15 | 17 |  | 40% | W15: 40%; W16: 40%; W17: 40%
7.2 | Server Deployment & Database Migration (Production) | DevOps / Lead | 16 | 17 |  | 10% | W16: 10%; W17: 10%
7.3 | User Manual, Librarian Guides & Video Demonstration | Technical Writer | 17 | 18 |  | 0% | bar: W1 to W18
7.4 | Final Capstone Oral Defense & Product Handover | Capstone Team & Panel | 18 | 18 |  | 0% | W18: ◆ MILESTONE
OVERALL PROJECT PROGRESS (Weighted Average):

## Legend & Milestone Guide
Item / Phase | Theme Color | Status / Meaning | Target Weeks
Phase 1: Project Initiation & Requirements | SAMPLE COLOR | Planning, feasibility, SRS baseline | Weeks 1 - 3
Phase 2: Architecture & UI/UX Design | SAMPLE COLOR | DB ERD, API specs, Figma mockups | Weeks 3 - 6
Phase 3: Backend & Database Engine | SAMPLE COLOR | Express APIs, Auth, Borrowing Logic | Weeks 6 - 11
Phase 4: Frontend Client & Dashboards | SAMPLE COLOR | Student catalog & Librarian tools | Weeks 7 - 13
Phase 5: Advanced Features & WebSockets | SAMPLE COLOR | QR scanner, notifications, map guidance | Weeks 12 - 15
Phase 6: QA, System Testing & UAT | SAMPLE COLOR | Integration test, user trial, bug fixes | Weeks 14 - 17
Phase 7: Final Defense & Deployment | SAMPLE COLOR | Manuscript, production deploy, defense | Weeks 15 - 18
Completed Task Bar (✓) | SAMPLE COLOR | Fully accomplished item (100%) | N/A
Capstone Milestone Marker (◆) | SAMPLE COLOR | Critical defense and evaluation milestone | W3, W6, W14, W18